## ورقة1
ID | As a... | I want to be able to... | So That... | Priority | Sprint | Status | Date DD/MM/YYYY
1 | User | Sing Up | I can write my stories and interact with other users. | P1 | 1 | Done | 04/03/2024 - 10/03/2024
2 | User | Sing In | I can write my stories and interact with other users. | P1 | 1 | Done | 04/03/2024 - 10/03/2024
3 | User | Write a story | I can save and publish it later. | P1 | 1 | Done | 04/03/2024 - 10/03/2024
4 | User | Edit my story text style | My story can be more clear and attractive. | P1 | 1 | Done | 04/03/2024 - 10/03/2024
5 | User | Save my story | I can get back to it and continue from where I stopped. | P1 | 1 | Done | 04/03/2024 - 10/03/2024
6 | User | Publish my story | I can make it visible for everyone and comment, rate, and give me their feedback. | P1 | 1 | Done | 04/03/2024 - 10/03/2024
7 | User | top stories | I can see the stories that have the highest rate. | P1 | 1 | Done | 04/03/2024 - 10/03/2024
8 | User | Visit users profile | I can read their stories, communicate with them, and interact with them. | P1 | 2 | Done | 10/03/2024 - 24/03/2024
9 | User | Reset my password | I can recover my account if I lose the account password. | P1 | 2 | Done | 10/03/2024 - 24/03/2024
10 | Owner | Account Verification | I can make sure that email is actually for that user. | P1 | 2 | Done | 10/03/2024 - 24/03/2024
11 | Owner | 404 page | If the user messed up the URL will be routed to this page | P1 | 2 | Done | 10/03/2024 - 24/03/2024
12 | Guest | read stories | I can read stories without signing up | P1 | 2 | Done | 10/03/2024 - 24/03/2024
13 | User | Edit My profile info. | I can edit my about, display name, and image. | P3 | 3 | Done | 27/03/2024 - 04/04/2024
14 | User | Story read page | I can read the stories and interact with it(rate it, leave a comment, or share it) | P2 | 3 | Done | 27/03/2024 - 04/04/2024
15 | User | Comment and rate | I can give my opinion about the story and have discussions with other users | P1 | 3 | Done | 27/03/2024 - 04/04/2024
16 | User | help center | If I have any problem I can contact the help center and they will help me | P3 | 3 | Done | 27/03/2024 - 04/04/2024
17 | User | Block/Mute | If any user announced me I can stop them | P2 | 3 | Done | 27/03/2024 - 04/04/2024
18 | User | logout | log out from a specific device or all devices | P1 | 3 | Done | 27/03/2024 - 04/04/2024
19 | User | Follow other users | I can interact with them | P1 | 3 | Done | 27/03/2024 - 04/04/2024
20 | User | Edit my user settings | I can change my profile from public to private and via versa, edit my personal information and my profile information. | P2 | 3 | Done | 27/03/2024 - 04/04/2024
21 | User | Search for a story | I can get the stories that I'm interested in and I want to read. | P1 | 3 | Done | 27/03/2024 - 04/04/2024
22 | User | sorted stoeis | I can explore the stories via the genres, views, ratings, etc. | P3 | 4 | Done | 04/04/2024 - 20/04/2024
23 | User | Delete or disable my account | I don’t share anymore of my personal information | P3 | 4 | Done | 04/04/2024 - 20/04/2024
24 | User | I want a Persistent Login | My account is secured | P1 | 4 | Done | 04/04/2024 - 20/04/2024
25 | User | browse in multi-languages | I can understand everything | P1 | 4 | Done | 04/04/2024 - 20/04/2024
26 | User | Have a reading list | I can remember it later | P1 | 4 | Done | 04/04/2024 - 20/04/2024
27 | User | have a list of my works | I can come back anytime and edit it | P1 | 4 | Done | 04/04/2024 - 20/04/2024
28 | User | Maintenance page | I know if im doing something wrong or the servers are down | P1 | 4 | Done | 04/04/2024 - 20/04/2024
29 | User | Search not found page | so that I know that there is no result for my search | P1 | 4 | Done | 04/04/2024 - 20/04/2024
30 | User | Dark theme | I can feel more comfy | P3 | 5 | to be started |  | احمد
31 | User | Chat with other users | Make new friends and work together on stories | P2 | 5 | to be started |  | عبود
32 | User | Share my stories list | Everyone that has the same mindset can see it or read it with me | P3 | 5 | to be started |  | عمر
33 | User | Edit my stories after publishing | As a user I want to be able to edit my story after I publish it | P2 | 5 | Done
34 | User | Write collaboratively | I can write a story with my friends or users from the community. | P1 | 5 | Done | 20/04/2024-20/5/2024 | امجد وعمر
35 | User