## ورقة1
ID | As a... | I want to be able to... | So That... | Priority | Sprint | Status
1 | User | Sing Up | I can write my stories and interact with other users. | P1 | 1 | Done
2 | User | Sing In | I can write my stories and interact with other users. | P1 | 1 | Done
3 | User | Write a story | I can save and publish it later. | P1 | 1 | Done
4 | User | Edit my story text style | My story can be more clear and attractive. | P1 | 1 | Done
5 | User | Save my story | I can get back to it and continue from where I stopped. | P1 | 1 | Done
6 | User | Publish my story | I can make it visible for everyone and comment, rate, and give me their feedback. | P1 | 1 | Done
7 | User | top stories | I can see the stories that have the highest rate. | P1 | 1 | Done
8 | User | Visit users profile | I can read their stories, communicate with them, and interact with them. | P1 | 2 | Done
9 | User | Reset my password | I can recover my account if I lose the account password. | P1 | 2 | Done
10 | Owner | Account Verification | I can make sure that email is actually for that user. | P1 | 2 | Done
11 | Owner | 404 page | If the user messed up the URL will be routed to this page | P1 | 2 | Done
12 | User | Edit My profile info. | I can edit my about, display name, and image. | P3 | 3 | In progress
13 | User | Write collaboratively | I can write a story with my friends or users from the community. | P1 | 3 | In progress
14 | User | Edit my user settings | I can change my profile from public to private and via versa, edit my personal information and my profile information. | P2 | 3 | In progress
15 | User | Search for a story | I can get the stories that I'm interested in and I want to read. | P1 | 3 | In progress
16 | User | Story read page | I can read the stories and interact with it(rate it, leave a comment, or share it) | P2 | 3 | In progress
17 | User | Inbox messages button | I can easily see if i have any new messages. | P2 |  | to be started
18 | User | Translate button | I can change the website language. | P2 |  | to be started
19 | User | sorted stoeis | I can explore the stories via the genres, views, ratings, etc. | P3 |  | to be started
20 | User | Block/Mute | If any user announced me I can stop them | P2 |  | to be started
21 | User | Chat with other users | Make new friends and work together on stories | P2 |  | to be started
22 | User | Comment and rate | I can give my opinion about the story and have discussions with other users | P1 |  | to be started
23 | User | Delete or disable my account | I don’t share anymore of my personal information | P3 |  | to be started
24 | User | Create stories list | I can come back anytime and find it easily | P1 |  | to be started
25 | User | Share my stories list | Everyone that has the same mindset can see it or read it with me | P3 |  | to be started
26 | User | Go the help page | If I have any problem I can contact the help center and they will help me | P3 |  | to be started
27 | User | Edit my stories after publishing | As a user I want to be able to edit my story after I publish it | P2 |  | to be started
28 | Writer | track my stories spread in the community | I can get some feedback on stories and the way I write | P3 |  | to be started
29 | User | logout | log out from a specific device or all devices | P1 | 3 | In progress
30 | User | Follow other users | I can interact with them | P1 | 3 | In progress
31 | User | Listen to the stories | I can do it while like i'm at the gym or something | P3 |  | to be started
32 | User | I want a Persistent Login | My account is secured | P1 |  | to be started
| Guest | read stories | I can read stories without signing up | P1 | 2 | Done
| User | browse in multi-languages | I can understand everything | P1 |  | to be started